## Apr-02
Start | Finish |  | ______________________________________________ | Person | Result
| 2002-03-01 | Ö | FPDP ordered and received. (Faster transfer from Mercury to vmesparc)
|  | Ö | Full set of CPUs (21) put into operation. 200 Hz achieved (w/o FASTBUS)
| 2002-04-01 | 1/2 | Support for online monitoring
| 2002-04-01 | Ö | Integration of FASTBUS.
| 2002-04-23 | Ö | DAQ rehearsal
| 2002-04-01 | Ö | New vmesparc (Faster disk transfer).
| 2002-04-01 |  | New Mercury OS.
| 2002-04-01 | Ö | FPDP installed. |  | 43 MB/s
| 2002-04-01 |  | PO for more fibers/crates
| 2002-05-01 | Ö | Optimization of Mercury timing. Goal: 300 Hz |  | 400 Hz
| 2002-06-01 |  | Trigger detectors installation
| 2002-07-01 |  | Trigger/DAQ integration.
Installation of crates/fibers.
| 2002-08-01 |  | Trigger integration. (need outside groups at BNL)
| 2002-09-01 |  | Overall optimization. Goal: 500 Hz.

## Sep-02
[5 empty] | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
| Task | Person |  | 2002-06-24 | 2002-07-01 | 2002-07-08 | 2002-07-15 | 2002-07-22 | 2002-07-29 | 2002-08-05 | 2002-08-12 | 2002-08-19 | 2002-08-26 | 2002-09-02 | 2002-09-09 | 2002-09-16 | 2002-09-23 | 2002-09-30 | 2002-10-07 | 2002-10-14 | 2002-10-21 | 2002-10-28 | 2002-11-04 | 2002-11-11 | 2002-11-18 | 2002-11-25 | 2002-12-02 | 2002-12-09 | 2002-12-16 | 2002-12-23 | 2002-12-30
1 | Implementation of the FPDP link in DAQ | AS
2 | Overhaul of the DMU crates. Fixing FEC errors. | PK
3 | Reading FASTBUS and VME crates directly to Mercury | AS
4 | Debugging of a VME board | PK
5 | Phat classes for online monitoring and offline | AS
6 | Increasing Si hardware limit above 500 Hz | PK
7 | Redistribution of DMUs between crates | PK | AS
8 | Optimization of workers' load in Mercury | PK | AS
9 | Learning FPGA | AS
10 | Spectrig logic module XLM72 implementation in the DAQ | AS
11 | Phasing out phobosx. Using phobosun (Ultra5) instead. | AS
12 | Overall DAQ optimization. Goal: 500 Hz. | AS
13 | Disk array upgrade. Goal: 1.2 TB, 60 MB/s from Mercury to disk | AS
14 | Preparation for 0 suppression. Adding Huffman+RLE format | AS
15 | System maintenance | AS
| DAQ ready | AS
Note on B13: Starts when it will be purchased/delivered
Note on B14: It became difficult to keep the Ultra 3000 alive. The idea is to use Ultra5, currently used as DAQ X-Term.
Note on B16: It will start when new disks and enclosure are purchased
Note on B17: RLE - run length encoding Combination of the Huffman and RLE make it possible to use the same data format for both compressed and zero suppressed data
Note on C4: Andrei Sukhanov
Note on C5: Piotr Kulinich
not allocated
not allocated
Planned
Still needed
Spent
Done
Done
Done
Done

## Sheet1
[5 empty] | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
| Task | Person |  | 2002-06-24 | 2002-07-01 | 2002-07-08 | 2002-07-15 | 2002-07-22 | 2002-07-29 | 2002-08-05 | 2002-08-12 | 2002-08-19 | 2002-08-26 | 2002-09-02 | 2002-09-09 | 2002-09-16 | 2002-09-23 | 2002-09-30 | 2002-10-07 | 2002-10-14 | 2002-10-21 | 2002-10-28 | 2002-11-04 | 2002-11-11 | 2002-11-18 | 2002-11-25 | 2002-12-02 | 2002-12-09 | 2002-12-16 | 2002-12-23 | 2002-12-30
1 | Implementation of the FPDP link in DAQ | AS
2 | Overhaul of the DMU crates. Fixing FEC errors. | PK
3 | Reading FASTBUS and VME crates directly to Mercury | AS
4 | Phat classes for online monitoring and offline | AS
5 | Increasing Si hardware limit above 500 Hz | PK
6 | Redistribution of DMUs between crates | PK | AS
7 | Optimization of workers' load in Mercury | PK | AS
8 | Learning FPGA | AS
9 | Spectrig logic module XLM72 implementation in the DAQ | AS
10 | Phasing out phobosx. Using phobosun (Ultra5) instead. | AS
11 | Overall DAQ optimization. Goal: 500 Hz. | AS
12 | Disk array upgrade. Goal: 1.2 TB, 60 MB/s from Mercury to disk | AS
13 | Preparation for 0 suppression. Adding Huffman+RLE format | AS
14 | System maintenance | AS
| DAQ ready | AS
Note on B12: Starts when it will be purchased/delivered
Note on B13: It became difficult to keep the Ultra 3000 alive. The idea is to use Ultra5, currently used as DAQ X-Term.
Note on B15: It will start when new disks and enclosure are purchased
Note on B16: RLE - run length encoding Combination of the Huffman and RLE make it possible to use the same data format for both compressed and zero suppressed data
Note on C4: Andrei Sukhanov
Note on C5: Piotr Kulinich
not allocated
not allocated
Planned
Still needed
Spent
Done
Done
Done
Done
Done