## Slide 1: Status and plans of DAQ and TOF upgrades

## Slide 2: DAQ Upgrade
Silicon
FrontEnd
Mercury
FPDP
FPDP
VME
Sun
Sun
GigaBit
HPSS
FPDP
TK 200
GigaBit
HPSS
No modifications in the data collecting subsystems
Phase out the Sun: ultrasparc and phobosx
Dedicated data recorder instead of a general purpose workstations
Gigabit Ethernet from Linux to HPSS.
Goal
Accepted triggers rate: 500 Hz, 50 MB/s
Dead time: 1.4 ms
Bottleneck: Silicon @ 800 Hz
FASTBUS
VME
PhTiMeS

## Slide 3: DAQ Schedule of 6/25
PO for TK200. Waiting for approval from the head of the Procurement Office.
FASTBUS. Done: Debugging of the cable link to replace Ethernet.
To do: Faster data taking. Improved reliability.
Silicon. Done: nothing.
To do: Reliability at higher speed (1.4 ms dead time). Cannot be done without Low Voltage.

## Slide 4: Interconnection tasks
Replacing Ethernet link with RS485 cable. FASTBUS->VME->(PhTiMeS)->Mercury Necessary with new Data Recorder.
Debugging of the point-to-point connection finished. VME block data transfer works (20 MB/s). Multi-drop protocol developed.
Implementation in the FASTBUS and VME DAQ crates. Implementation in the Mercury crate.
Event building in Mercury. 90% finished.

## Slide 5: Silicon readout tasks
Improvement of the Silicon readout.
Goal: Reliable data taking with 1.4 ms deadtime
All code are there.
Debugging of the system with dummy receiver on the FPDP link.
This requires Low Voltages on FECs

## Slide 6: New Data Recorder tasks
PFTP for Linux.
Preparation for the new Data Recorder (TK200).
Data mover goes Linux.
Reading from the Data Recorder.
Gigabit Ethernet with new adapters.
Writing data to the Data Recorder
Single data stream (from Mercury crate). No event building.

## Slide 7: PhTiMeS schedule

## Slide 8: PhTDC input

## Slide 9: PhTDC TDC

## Slide 10: PhTDC Xilinx

## Slide 11: PhTDC VME

## Slide 12: PhTiMeS Tasks
Schematic of the PhTDC is ready
RS485 cable link to Mercury crate.
PCB layout of the PhTDC is 50% ready
PhLoM logic module for PhTiMeS can be implemented using existing PCDP boards. New PhLoM is not time-critical.
Most components are available immediately. Max lead time = 4 weeks.
HPTDCS chips are not in hand yet. Several thousands are waiting to be tested at CERN. They aware of our order of 80 chips.
VME crate with MVME commissioned.
Software implementation to the existing DAQ.
Testing software.
Synchronization and setup. PhLoM programming
Readout software
Xilinx programming of the PhTDC – 90% of the debugging process.
Impossible to get visas in less than 6 months.
Considering remote help from Dudna during debugging.
One PhTDC probably need to be shipped to Dubna.
Debugging of the PhTiMes

## Slide 13: Supporting slides

## Slide 14: Big River TK200 from Conduant

## Slide 15: TK200
Big River TK200 Specifications
Max. Data Rate 200 Mbytes/sec ~ sustained
Max. Disk Drives (16) EIDE ATA 100, packaged in easily removable drive modules. Total 3.2 TB.
Two Gigabit Ethernet ports
Max. Duration 24/7 recording in Pendulum mode (addt'l modules required)
External Interface Front Panel Data Port (FPDP) ~ 50MHz at 32-bit
Power ATX 550W
Chassis Dimensions (5U) 9”H x 19”W x 26”D Rackmount
Operating Systems Windows NT/200/XP, Linux
Used in:
MIT - Haystack Observatory Mark 5 VLBI Data System